## Slide 1
County Waterford LDS: Early Cycle Evaluation

## Slide 2
Purpose of the Evaluation
What Is It?
A high-level, early-stage evaluation of the Waterford Local Development Strategy (LDS) 2023–2027, reviewing the first two years of delivery under the LEADER Programme.
Why Now?
The LDS specified reviews at two points – after two years and at programme end. This review focuses on progress and delivery rather than long-term results.
What Does It Cover?
Programme set-up, budget allocations, targeted calls, expressions of interest, project applications, stakeholder feedback, and recommendations for the remaining period.
Who Is It For?
The Local Community Development Committee (LCDC), the Local Action Group (LAG), the Implementing Partner (Waterford LEADER Partnership CLG), and the Department of Rural and Community Development and the Gaeltacht.
County Waterford LDS: Early Cycle Evaluation

## Slide 3
Programme Budget
County Waterford LDS: Early Cycle Evaluation
€6,338,235
Project Budget €4,569,308
Total Waterford allocation
2023–2027 LEADER Programme
13th of 26 county allocations
65%
Theme 1
Economic Development
€2,970,717
22%
Theme 2
Rural Infrastructure
€1,005,633
13%
Theme 3
Environment
€592,958
National LEADER budget trend (€ million total)
2007–2013 €425M
2016–2020 €250M
2023–2027 €180M

## Slide 4
Budget Allocations 2024 and 2025
County Waterford LDS: Early Cycle Evaluation
€1,097,178
Allocated in 2024
24% of total LDS budget
€981,828
Allocated in 2025
21.5% of total LDS budget
€2,079,006
Cumulative 2024–25
Across 8 of 11 strategic actions

## Slide 5
Targeted Calls Summary
County Waterford LDS: Early Cycle Evaluation
Four targeted calls issued 2024 - 2026, total advertised budget: c.€8.6 million
Date
Budget
EoIs
Applications
Approved
Call 1
Feb 2024
€2,266,324
63
22
13
Call 2
Nov 2024
€2,032,254
47
10
9
Call 3
Jul 2025
€2,101,124
37
6
4
Call 4
Jan 2026
€2,193,606
–
–
–

## Slide 6
Application Funnel – Calls 1 to 3
County Waterford LDS: Early Cycle Evaluation
Chart: 
| EoIs Received | Eligible EoIs | Applications Received | Applications Approved | Projects Proceeded
Count | 147 | 123 | 38 | 28 | 26
147
Total EoIs received
(Calls 1–3)
31%
Conversion: EoI
to application
74%
Approval rate
(of applications)

## Slide 7
Project Promoter Consultation
County Waterford LDS: Early Cycle Evaluation
✓ Implementer Staff
Staff consistently praised as excellent, approachable, helpful and positive. Strong relationships developed across multiple applications.
✓ Funding Value
All promoters agreed that funding was essential for rural businesses and communities, particularly for capital and equipment investment.
✗ Application Process
Widely viewed as overly difficult and time-consuming. Extensive paperwork, repeated verification checks, and a perception of operating in a spirit of mistrust were cited.
✗ eTenders Procurement
Particularly negative feedback received. Promoters reported difficulty registering and confusing guidance. One applicant withdrew after losing significant time using the system.
✓ Promoter Support
Promoters recognised that strict procedures are part of managing public funding and noted that the Implementer’s staff made strong efforts to support applicants.
✓ Process
The incremental stages (information sessions, expression of interest and application requirements workshop) helped applicants decide whether they are ready or should consider other funding options.

## Slide 8
Project Promoter Consultation
County Waterford LDS: Early Cycle Evaluation
Roll-out Proceeding Well
All consultees noted the programme had proceeded well, with effective cooperation among the Financial Partner, Implementer, Independent Evaluation Committee, and the LAG.
Targeted Calls Effective
Targeted calls were seen to focus efforts on strategic areas and explain the programme's purpose, contributing to higher-quality submissions.
IEC Process Open & Transparent
The project evaluation process was open and transparent. Decisions were based only on information provided and assessed against job creation, sustainability, and value for money.
eTenders a Significant Hurdle
For those unfamiliar with eTenders, this was considered a significant challenge often requiring the engagement of professional expertise, adding cost to applicants.
Claims Expected to Rise
Consultees agreed that an increase in claims is expected over the next nine months, with two targeted funding calls planned for 2026 compared to one in 2025.
Competition for Funding
LEADER operates in a crowded funding space. Other available supports (including from the Local Authority) make it challenging for some promoters to identify the correct avenue.

## Slide 9
Administration and File Management
County Waterford LDS: Early Cycle Evaluation
A random sample of application files was reviewed spanning multiple themes, promoter types, and geographic areas
Well-structured, consistent administrative process across all reviewed files.
Clear evidence that procurement procedures were followed throughout.
Business plans present where required, demonstrating consideration of long-term viability.
Very high level of compliance with LEADER Programme requirements confirmed.
IEC decisions arrived at by agreement, with a broad range of sector expertise represented.
Thorough paper trail: minutes and evaluation reports of consistent, high standard.
Files stored securely; no recorded security breaches to date.

## Slide 10
Promoter Challenges & Programme Performance
County Waterford LDS: Early Cycle Evaluation
Co-Finance
Securing sufficient co-finance is one of the main reported challenges. LEADER funding is paid retrospectively, necessitating bridging finance and creating cash flow risk.
Public Procurement
eTenders must now be used for supplies contracts over €50,000 ex VAT and works over €200,000 ex VAT. Many promoters are unfamiliar with the system.
Statutory Permissions
Many projects require planning permission or other statutory approvals, causing delays that can affect funding deadlines and add professional service costs.
Competing Grants
Other grant programmes with less demanding application processes are more attractive to some promoters, contributing to a decline in EoIs.
Programme Performance after Call 3 | As of December 2025
7th
National expenditure
ranking (of 33 LAGs).
21%
Total programme budget
claimed by January 2026.
€2.49M
Remaining to allocate
by programme end.
25
Projects supported
across Calls 1–3.
€1,824,146.93 remaining after 4th Call. 5th Call advertised on 30th June 2026 (€1,820,310.93)

## Slide 11
Conclusions and Recommendations
County Waterford LDS: Early Cycle Evaluation
Overall Finding: The Waterford LDS is being implemented professionally. The approach to project identification and selection is appropriate, and all partners – the Implementing Partner, IEC, Financial Partner, and LAG – are effectively carrying out their respective roles.
Business Sentiment
Encourage smaller-scale, lower-risk projects in current conditions. Monitor rising energy costs as a potential driver of interest in Theme 3 (Environment). Consider inflation impact on grant values.
Programme Structure
The national sub-theme structure is considered overly prescriptive; not possible to change within the current programme but should be raised for future iterations.
Programme Performance
Waterford ranks 12th nationally (31/03/26). Close monitoring of allocations and claims is essential: €2.49M must be invested over the remaining programme period through targeted and open calls.
Application Process
Consider additional support for promoters unfamiliar with LEADER requirements. Explore simplification with DRCDG, particularly for community groups and small businesses.

## Slide 12
Conclusions and Recommendations
County Waterford LDS: Early Cycle Evaluation
Overall Finding: The Waterford LDS is being implemented professionally. The approach to project identification and selection is appropriate, and all partners – the Implementing Partner, IEC, Financial Partner, and LAG – are effectively carrying out their respective roles.
Promoter Challenges
Targeted actions needed on co-finance access, eTenders support, statutory permissions awareness, and earlier signposting of competing grant schemes.
Budgetary Allocation
€2,491,451.97 remains to be allocated. Continued vigilance through targeted calls and potential open calls as the programme approaches conclusion in 2027 is essential.

## Slide 13
County Waterford LDS: Early Cycle Evaluation